ACTION PLAN FOR INTEGRATION OF ETHNIC MINORITIES UNTIL 2020

| Priority 1. Improving the level of educational of the representatives of ethnic minorities – guarantee for successful and sustainable integration |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| REF. № | ACTIVITY | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 1.1. Increasing the scope of children from ethnic minorities in pre-school and primary school education |  |  |  |  | 1 800 000 |
| D.1.1 | Major renovations, expansion and improvement of ODZ, TSDG | Aksakovo Municipality | 2015 – 2020 | municipal budget state budget |  |
| D.1.2 | Development and implementation of a program for encouraging responsible parental attitude towards educational integration and acquiring particular skills and attitudes | Aksakovo Municipality | 2015-2018 | Euro funds |  |
| D.1.3. | Creation and implementation of training program which offers additional activities for children in early childhood (3-6 years) in order to facilitate their inclusion in the educational process in the future | Aksakovo Municipality | 2015-2018 | Euro funds |  |
| D.1.4 | Creating a program and conducting training modules in ODZ and TSDG on violence prevention | Aksakovo Municipality | 2015-2018 | Euro funds |  |
| D.1.5 | Organizing campaigns to raise awareness of parents from ethnic minorities regarding the benefits of pre-school education | Aksakovo Municipality ,NGO | 2015-2020 | Euro funds |  |
| D.1.6 | Involvement of parents of children and pupils from ethnic minority groups in school boards and / or public councils | Aksakovo Municipality | 2015 - 2020 |  |  |
| D.1.7 | Opening of school centers for children who have difficulties studying because their parents are illiterate and cannot help them | Aksakovo Municipality | 2015 - 2020 | Euro funds |  |
| Specific objective 1.2. Minimizing the number of drop-out students in primary education |  |  |  |  | 2 140 000 |
| D.1.8 | Construction of additional hulls in secondary schools in villages inhabited mainly by children from ethnic minorities, incl. indoor sports halls |  | 2015 - 2018 | municipal budget Rural Development Programme |  |
| D.1.9 | Development of a program for educational integration of children from ethnic minorities | Aksakovo Municipality | 2015 - 2016 | municipal budget OP Human Resources Development |  |
| D.1.10 | Organizing campaigns for raising awareness of parents from ethnic minorities about the benefits of primary education for reducing dropouts of schools | Aksakovo Municipality , NGO | 2015 - 2020 | Euro funds |  |
| D.1.12 | Opening school centers for children who have difficulties studying because their parents are illiterate and cannot help them | Aksakovo Municipality , schools, NGO | 2015 - 2020 | Euro funds |  |
| D.1.13 | Involvement of parents of children and pupils from ethnic minority groups in school boards or public councils | Aksakovo Municipality , schools, NGO | 2015 - 2020 | Euro funds |  |
| D.1.14 | Encouraging the inclusion of students from vulnerable ethnic minorities in school parliaments and interest clubs for optional subject | Aksakovo Municipality , schools, NGO | 2015 - 2020 | Euro funds |  |
| D.1.15 | Opening of school centers for children from ethnic minorities expelled from school with the aim of organizing their free time on a daily basis | Aksakovo Municipality , NGO | 2015 - 2020 | Euro funds |  |
| D.1.16 | Reintegration of students who have left school by providing opportunities for independent study, evening classes and alternative forms of extracurricular education | Aksakovo Municipality , schools, NGO | 2015 - 2020 | Euro funds |  |
| Specific objective 1.3 Training and education of the illiterate representatives of ethnic minorities with the aim of integrating them into the labor market |  |  |  |  | 500 000 |
| D.1.17 | Providing conditions and services for increasing qualification and access to employment for Roma | Aksakovo Municipality | 2015 - 2020 | municipal budget OP Human Resources Development |  |
| D.1.18 | Educating Roma adults in order to raise their literacy | Aksakovo Municipality Employment Agency, NGOs, private sector | 2015 – 2020 | Euro funds, private funding |  |
| Specific objective 1.4. Improving the qualification of pedagogical specialists for interaction in multicultural educational environment |  |  |  |  | 150 000 |
| D.1.19 | improving the qualification of teachers, principals and other educational professionals for working in multicultural environment in order to prevent children’s dropping out of school | Aksakovo Municipality , schools, NGO | 2015 - 2020 | OP Human Resources Development , Euro funds |  |
| D.1.20 | Increasing the capacity of school teams for the development and implementation of project proposals | Aksakovo Municipality , schools, NGO | 2015 – 2020 | OP Human Resources Development , Euro funds |  |
| D.1.21 | Increasing the capacity of school teams to implement good practices of NGOs for conducting extracurricular activities to include and stimulate children from ethnic minorities for educational integration | Aksakovo Municipality , schools, NGO | 2015 - 2020 | OP Human Resources Development , Euro funds |  |
| D.1.22 | Inclusion of additional component "integration of pupils from ethnic minorities" in the delegated school budgets | Aksakovo Municipality | 2015 - 2020 | municipal budget |  |
| Specific objective 1.5. Increasing the percentage of Roma with secondary and higher education and their successful realization on the labor market. |  |  |  |  | 80 000 |
| D.1.23 | Providing opportunities for practices for students from disadvantaged ethnic minorities in a real work environment (internships) | Aksakovo Municipality, NGOs, private sector | 2015 - 2020 | OP Human Resources Development , Euro funds , private funding |  |
| D.1.24 | Providing municipal scholarships for outstanding students from vulnerable ethnic groups and access to hostels | Aksakovo Municipality | 2015 - 2020 |  |  |
| D.1.25 | Development and implementation of program for school mediation | Aksakovo Municipality , schools, NGO | 2015 – 2018 |  |  |
| PRIORITY 2. Access to healthcare and social integration of vulnerable ethnic minorities |  |  |  |  |  |
| Ref. № | Activity | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 2.1. Providing conditions for adequate and equitable medical care and health prophylactics of the representatives of all ethnic groups in Aksakovo |  |  |  |  | 50 000 |
| D.2.1 | Carrying out prophylactic examinations, immunizations and diagnostics by mobile teams in settlements with compact population of ethnic minorities | Aksakovo Municipality, RHIF Regional Health Insurance Fund | 2015 - 2020 | Euro funds , NF |  |
| D.2.2 | Organizing information campaigns among parents about the importance of registering children with a General Practitioner - GP | Aksakovo Municipality , NGO | 2015 - 2020 | Euro funds , NF |  |
| Specific objective 2.2. Increasing the percentage of health insured people among vulnerable ethnic groups. |  |  |  |  | 50 000 |
| D.2.3 | Raising the awareness of the disadvantaged ethnic minorities regarding their rights and obligations as patients and the kind of medical services provided | NGO | 2015 - 2020 | Euro funds |  |
| Specific objective 2.3. Increasing health awareness and knowledge of the representatives of ethnic minorities. Training healthcare professionals for work in multicultural environment |  |  |  |  | 70 000 |
| D.2.4 | raising health awareness by conducting information campaigns | NGO | 2015 - 2020 | Euro funds |  |
| D.2.5 | Appointment and validation of health mediator as a coordinator between health institutions and people from ethnic groups | Aksakovo Municipality | 2015 - 2015 | Municipal budget Euro funds |  |
| D.2.6 | Cooperation and strengthening cooperation between GPs and the mediators | Aksakovo Municipality, RHIF Regional Health Insurance Fund | 2015 - 2020 | Municipal budget , Euro funds |  |
| Specific objective 2.4. Improving care for pregnant women, newborns and children in pre-school and school age |  |  |  |  | 50 000 |
| D.2.7 | Organization of consulting rooms in settlements with predominantly Roma on sexual and reproductive health, family planning and prevention of sexually transmitted infections | Aksakovo Municipality , NGO | 2015 - 2020 г. | Euro funds |  |
| PRIORITY 3. Housing conditions and urbanization of areas densely populated by ethnic minorities |  |  |  |  |  |
| Ref. № | Activity | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 3.1. Improving the technical infrastructure of villages and neighborhoods inhabited by compact population of ethnic minorities |  |  |  |  | 13 400 000 |
| D.3.1 | Developing Detailed Regulation Plans for urban areas - settlement formations |  |  | Municipal budget, OP Rural Development |  |
| D.3.2 | Improvement of water supply and sewerage network in towns and villages inhabited by compact population of ethnic minorities |  |  | Operational program Environment- OPE , OP Rural Development |  |
| D.3.3 | Rehabilitation of street network in the town of Ignatievo, the village of Slanchevo and the village of Kichevo |  |  | Municipal budget, OP Rural Development |  |
| D.3.4 | Construction and maintenance of buildings for public use - community centers, libraries |  |  | Municipal budget, OP Rural Development |  |
| D.3.5 | Construction of facilities of the social infrastructure |  |  | Municipal budget, OP Rural Development |  |
| D.3.6 | Upgrading the heating installation of public buildings in the town of Ignatievo to work with gas |  |  | Municipal budget , OP Rural Development |  |
| D.3.7 | Renovation of the central part (Square), creating area for recreation and children’s playgrounds in settlements with compact Roma population |  |  | Municipal budget , OP Rural Development |  |
| D.3.8 | Correction and deepening of the gully in the town of Ignatievo |  |  | OPE , OP Rural Development |  |
| Specific objective 3.2. Improvement of living conditions of disadvantaged Roma and other vulnerable families. |  |  |  |  | 200 000 |
| D.3.9 | Development of methodology and evaluation criteria for the selection of people in need of social housing | Aksakovo Municipality , NGO | 2015 - 2017 | Euro funds |  |
| D.3.10 | Stimulating the participation of people from ethnic minorities in activities for improving their housing conditions, maintenance and hygiene | NGO | 2015 - 2020 | Euro funds |  |
| D.3.11 | Continuing the process of developing cadastral maps and cadastral records covering areas densely populated by ethnic minorities |  |  | NF |  |
| Specific objective 3.3. Construction and rehabilitation of social housing. |  |  |  |  | 100 000 |
| D.3.12 | Development of methodology with criteria for assessing the selection of people in need of social housing | Aksakovo Municipality , NGO | 2015 - 2017 | Euro funding |  |
| D.3.13 | Involvement of NGOs and some distinguished people from the community so that to establish behavioral models for forming an attitude of good and responsible owner after being granted the right to use immovable property | NGO | 2015 – 2018 | Euro funding |  |
| PRIORITY 4. Increasing employment and equal participation in the labor market of representatives of ethnic groups |  |  |  |  |  |
| Ref. № | Activity | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 4.1. Training and qualification of unemployed and low paid representatives of ethnic minorities |  |  |  |  | 350 000 |
| D.4.1 | Organizing vocational training courses for unemployed people, ethnic minorities, including traditional Roma crafts | Labour Office NGOs , private sector | 2015 – 2020 | Euro funding, NF, OP Human Resources Development, OP Rural Development |  |
| D.4.2 | Organizing training courses for unemployed people with higher education in computer literacy, entrepreneurship, preparation of business projects, starting and running own business, social activities and more. | Labour Office, Aksakovo Municipality, private sector | 2015 – 2020 | Euro funding, NF, OP Human Resources Development, private sector |  |
| D.4.3 | Providing opportunities for employment, including apprenticeship and internship after finishing training courses | Aksakovo Municipality, private sector | 2015 – 2020 | Euro funding, OP Human Resources Development, private sector |  |
| Specific objective 4.2. Motivation of inactive and discouraged people from ethnic minorities |  |  |  |  | 100 000 |
| D.4.4 | Promoting employment through engaging the unemployed people from ethnic minorities in programs and measures funded under the Law on Employment Promotion and the operational programs | Labour Office NGOs , private sector | 2015 – 2020 | NF, OP Human Resources Development, private sector |  |
| D.4.5 | Organizing meetings, seminars and information campaigns in order to motivate inactive and discouraged people from ethnic minorities | NGOs, Aksakovo Municipality | 2015 – 2020 | Euro funding |  |
| D.4.6 | Organizing training for employees of labor offices to acquire specific skills to work with representatives of the Roma population. | Labour office | 2015 – 2020 | NF, ОPAC |  |
| D.4.7 | Appointment of a labor mediator from ethnic minorities | Aksakovo Municipality | 2015 - 2017 |  |  |
| D.4.8 | Organizing seminars and Information campaigns to encourage employment of Roma in agriculture. | Labour office , NGOs , private sector | 2015 – 2020 | Euro funding, NF, OP Rural Development, private sector |  |
| Specific objective 4.3. Improving access to the labor market, increasing employment and incomes of the population from the ethnic groups |  |  |  |  | 200 000 |
| D.4.9 | opening outsourced jobs of the labor office or advisory receptions | Labour office | 2015 - 2020 | Euro funding |  |
| D.4.10 | opening centers for partnership between employees from the labor office, municipal administration, employers and organizations representing ethnic minorities | NGOs | 2015 - 2020 | Euro funding |  |
| D.4.11 | Inclusion of people from ethnic groups in national employment programs and measures | Labour office | 2015 – 2020 | NF, OP Human Resources Development, Private sector |  |
| D.4.12 | Organizing information days "open doors" introducing the opportunities for the private businesses to apply for projects | Aksakovo Municipality | 2016 – 2020 | Euro funding |  |
| PRIORITY 5. Rule of law and non-discrimination |  |  |  |  |  |
| Ref. № | Activity | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 5.1. Fighting discrimination, raising awareness of fundamental human rights and legal culture of ethnic minorities |  |  |  |  | 70 000 |
| D.5.1 | Training police officers to work effectively in multicultural environment | Regional police Department | 2015 - 2017 | Euro funding, National funding |  |
| D.5.2 | Information campaigns to raise awareness regarding the legal rights and culture of ethnic minorities | Aksakovo municipality, NGO | 2015 - 2020 | Euro funding |  |
| D.5.3 | Information campaigns to combat intolerance and stereotypes towards ethnic minorities | Aksakovo municipality, NGO | 2015 - 2020 | Euro funding |  |
| Specific objective 5.2. Providing conditions for the participation of ethnic minorities in the process of decision-making in developing and implementing local integration policies |  |  |  |  | 10 000 |
| D.5.4 | Encouraging the participation of the structures of civil society engaged with the problems of Roma inclusion in the process of formation, implementation and monitoring of the integration policies. | NGO | 2015 - 2020 | Euro funding |  |
| Specific objective 5.3. Improving the efficiency of the police officers’ work in multicultural environment |  |  |  |  | 25 000 |
| D.5.5 | Taking preventive action against selling of drugs in Roma neighborhoods and districts with mixed population | Aksakovo municipality, Police Department , NGO | 2015 - 2020 | Euro funding , national funding |  |
| D.5.6. | Conducting preparation courses for young Roma wishing to work in the police: Bulgarian language, physical fitness and psychological fitness. | Aksakovo municipality | 2015 - 2020 | Euro funding , national funding |  |
| D.5.7 | Organization of seminars to enhance the efficiency of the Law enforcement officers in multiethnic environment in compliance with the standards on human rights. | Aksakovo municipality, Police Department , NGO | 2015 – 2020 | Euro funding , national funding |  |
| Specific objective 5.4. Implementation of joint actions of the police and the Roma community |  |  |  |  | 25 000 |
| D.5.8 | Organization of seminars and meetings in schools to raise awareness on the issues of aggression among adolescents, smoking, alcohol consumption, domestic violence and others. | NGO | 2015 – 2020 | Euro funds |  |
| Specific objective 5.5. Protecting the rights of Roma women |  |  |  |  | 25 000 |
| D.5.9 | Activities against abuse of parental authority and violation of the rights of Roma women due to the traditional Roma practices which make underage girls live like spouses | Aksakovo municipality, NGO | 2015 - 2020 | European funding |  |
| D.5.10 | Prevention concerning pressing problems of Roma women - early marriages and early births, abandoning of children in social homes , prostitution, etc. | Aksakovo municipality, NGO | 2015 - 2020 | European funding |  |
| PRIORITY 6. Culture and media |  |  |  |  |  |
| Ref. № | Activity | Responsible organization | Time period | Source of funding | Indicative value (leva) |
| Specific objective 6.1. Preservation and development of traditional for each ethnicity - culture, art and customs. Equal access to the social and cultural life of the municipality. |  |  |  |  | 60 000 |
| D.6.1 | Increasing the capacity of the employees in the centers for preserving, developing and dissemination of Roma culture | Aksakovo municipality, NGO | 2015 - 2017 | European funding |  |
| D.6.2 | Support for the expansion of community centers in areas with mixed ethnic population | Aksakovo municipality, NGO | 2015 - 2020 | European funding |  |
| D 6.3 | Inclusion of events that celebrate specific holidays of the ethnic minorities and traditional celebrations in the cultural calendar of the Municipality Aksakovo | Aksakovo municipality | 2015 - 2020 | European funding |  |
| D.6.4 | Providing support for individual and group participation of artists and performers of ethnic minorities in national competitions and festivals | Aksakovo municipality, NGO | 2015 - 2020 | European funding |  |
| Specific objective 6.2. Raising awareness about the Roma and their culture. |  |  |  |  | 30 000 |
| D.6.5 | Organizing training of the administration employees to increase their capacity in terms of cultural values and customs of various ethnic minorities. | Aksakovo municipality | 2015 - 2020 | Operational Program Administrative capacity OPAC |  |
| Specific objective 6.3. Presence of minority communities in the media. |  |  |  |  | 18 000 |
| D.6.6 | Development and distribution of information materials presenting the culture and traditions of ethnic minorities | Aksakovo municipality | 2015 - 2020 | European funding |  |
| D.6.7 | Training of representatives of press and electronic media to overcome existing stereotypes and negative attitudes | Aksakovo municipality | 2015 - 2020 | European funding |  |